## Sheet1
DMS QUERIES :
upload supported for doc,xls,tiff,tif,gif,png,pdf,odt,webp,ods,rtf,csv,jpg,txt,ppt formats
FUTURE ENHANCEMENT :
Deleted files should be deleted from repo folder too.
User previlege need to be given for admin.
Sl No | Task | Status
1 | Dashboard: Bookmark, checkout files, Recycle bin | Completed except Recycle bin
2 | Documents:Treeview: expand and collapse in folder icon and not in folder names
3 | Add Folder: enable enter key | Completed
4 | folder edit option not added (right click) | Completed
5 | add folder modal -> add loading text | Completed
6 | Upload files:delete icon should be added in upload modal | Completed
7 | if new files selected after selecting some files old selection got deleted. refer old dms. | Completed(but no of files has to be displayed properly)
8 | Properties update button -> automatic refresh, snackbar after updation | Completed
9 | properties file date should be same as fileview date | Completed
10 | in Fileview , files should be displayed based on created date. | Completed | 3
11 | In merge file modal, status should be cleared after merge. | Completed
12 | In split file modal, status should be cleared after split. | Completed
13 | In Fileview created At , time is not needed | Completed
14 | Stamp process taking more time and pdf viewer not refreshed
15 | Fileview version, version number is not changing, date format has to be changed,permalink not working | Completed but permalink has to be added
16 | if file is modified in fileview, version should be refreshed
17 | Split is not considering recently merged content
18 | fileview right click cut,checkout,bookmark and copy should accept multiple check files
19 | file view right click enable and disable checkin, checkout, add and delete bookmark
20 | file view right click edit option not needed | Completed | 2
21 | for checked out file no function should work except view, mainbar icons and right click options except check in should also be disabled | Completed | 1
22 | in bookmark and checkout fileview , automatic refresh need to be added | Completed | 4
23 | bookmark and checkout , if we left click properties should be viewed
24 | for checkout, properties update button should be disabled,version should be disabled
25 | checkin modal - loading should be added | Completed
26 | after checkin, checkout page should be automatically refreshed | Completed
27 | in boomark, delete menu should be disabled. All other menus should work
28 | In Search, file name should be accepted without extension
29 | In property update, during keywords update space is added in the front instead of back for keywords 2
30 | split file name -> remove words split
31 | file delete -> snackbar " are you sure you want to delete?" | Completed